## Sheet1
Requirement Specification
Req ID | Name of Req | Description | Priority | Who uses it? | Release/Week | Source
1 | Calculate distance of commute | Calculates distance from university to reccommending area | A | User | Release 1 (Week 2) | Open Trip Planner, tfigtfs, psm
2 | Collect data for protoytpe from D1 TO D3 | Collect different data like rent, amenities, commute distance, universities | A | Reccommendation Engine | Release 1 (Week 2) | Rent data - RTB, rent.ie, and daft.ie Amenitites - OSM (Open Street Map)
3 | Survey TUD students | Collect data from students studying in TUD | A | Crib Crew | Release 1 (Week 2) | Google forms
4 | Reccommending Area | Recommend top 3 dublin areas based on user preference | A | User | Release 1 (Week 3) | With the data collected
5 | Explaining the reccommendation | Explain the shorlist | B | User | Release 1 (Week 3) | Python
6 | Finalise Tech Stack | Choose feasible tools to run the engine | A | Crib Crew | Release 2 (Week 3) | Own research
7 | Collect data for protoytpe from D4 TO D15 | Collect different data like rent, amenities, commute distance, universities | A | Reccommendation Engine | Release 2 (Week 4) | Rent data - RTB, rent.ie, and daft.ie Amenitites - OSM (Open Street Map)
8 | Create UI design | Basic UI Building | A | User | Release 3 (Week 5) | Node.js
9 | Map view for district information | Create map view for different dublin districts | B | User | Release 3 (Week 5) | Node.js
10 | Improve code with new data | Update datasets in py file, and improve code based on it. | A | User | Release 3 (Week 5) | Python
11 | Build recommendation api | convert the recommendation engine into web api that website can send user preferences and receive the top 3 areas | A | Reccommendation Engine | Release 3 (Week 5) | Python
12 | Host Backend on Azure | Deployed the api on azure app so its available with public utl | A | User | Release 3 (Week 5) | azure
13 | Automatic deployment | automatically redeploy the backend when the code is pushed to the main branch of github | B | Crib Crew | Release 3 (Week 5) | github
14 | Connect frontend to backend | website sends users priority to api and displays the result | A | User | Release 3 (Week 6) | Node.js
15 | Validate user input | Reject invalid input and display error message | B | User | Release 3 (Week 6) | Python
16 | Handle missing area data | give a heads up to the user when an area is left out because data for their chosen accomodation type is missing | B | User | Release 3 (Week 6) | Python
17 | Find supermarkets in a particular area | Investigate and confirm number of supermarkets in each area | B | User | Release 3 (Week 6) | Manual verifiaction
18 | Find parks, gyms | Investigate and confirm number of parks in each area | B | User | Release 3 (Week 6) | Manual verifiaction
19 | Find cafes/restaurants | Investigate and confirm different types of cafes/restaurants in each area | B | User | Release 3 (Week 6) | Manual verifiaction
20 | Find pharmacies and hospitals | Investigate and confirm number of pharmacies and hospitals in each area | B | User | Release 3 (Week 6) | Manual verifiaction
21 | Display area demographics | Display useful Census demographic information about each area | B | User | Release 4 (Week 7) | Census dataset (CSO)
22 | International community | Show demographic community information from Census data | B | User | Release 4 (Week 7) | CSO
23 | Mobile responsive UI | Website properly works on phone,tablets,desktop | A | User | Release 4 (Week 8) | Non functional
24 | Make website more attractive | Design website attractive and attention grabbing | A | User | Release 4 (Week 8) | Non functional
25 | Initiate AI agent | Introduce AI chatbot for immediate info | C | User | Release 5 (Week 9)
26 | Add Voice Assistant function | Introduce Voice Assistant | C | User | Release 5 (Week 9)